By BrimerH.C.R. No. 64

HOUSE CONCURRENT RESOLUTION

WHEREAS, DalMac Construction Company, Inc., alleges that:

(1)  on February 15, 1993, DalMac Construction Company and Texas A&M University entered into a contract for  the construction of a recreational sports building;

(2)  almost immediately after work began, DalMac Construction Company discovered that the university's plans and specifications did not adequately describe the work, the plans frequently conflicted with the specifications, and it was impossible to construct the building from the plans and specifications;

(3)  DalMac Construction Company incurred several hundreds of thousands of dollars in additional expense because the university insisted on performance that exceeded the plans and specifications as initially requested;

(4)  in compliance with the procedures specified in the contract, DalMac Construction Company regularly notified the university and requested clarification of inadequacies, conflicts, and other problems, and in some instances the university did not respond for more than a year;

(5)  in compliance with the procedures specified in the contract, and as a direct result of design inadequacies and conflicts, DalMac Construction Company was forced to submit change proposals for time and money;

(6)  after numerous change proposals were denied or left unanswered, DalMac Construction Company used the dispute resolution procedure specified by the contract;

(7)  despite the obvious problems with the university's architectural plans and specifications, and despite the university's insistence on performance that exceeded the initial contractual requirements, DalMac Construction Company fully satisfied its contractual obligations, both as initially required and as subsequently modified at the insistence of the university;

(8)  the university refused to extend the construction date for more than 15 days during construction;

(9)  after construction was completed the university inexplicably granted two additional extensions of 43 and 17 days, setting December 20, 1994, as the adjusted date of completion, but these extensions were of little consequence since the project was 290 days beyond schedule due to problems with the plans;

(10)  DalMac Construction Company completed construction on or about November 17, 1995;

(11)  on or about October 16, 1995, DalMac Construction Company submitted to the vice chancellor of The Texas A&M University System a "Request for Equitable Adjustment," supported by project documents, which included requests for time and money, with the total claim at that time amounting to $2,412,575.66;

(12)  the vice chancellor summarily responded to the "Request for Equitable Adjustment" by indicating that the university was not responsible for the losses of DalMac Construction Company and its subcontractors regardless of cost;

(13)  there was no indication that the university reviewed the "Request for Equitable Adjustment," and both the rapidity and the content of the vice chancellor's response suggest that the university did not, in fact, review the "Request for Equitable Adjustment";

(14)  despite DalMac Construction Company's repeated proposal for a joint review of the plans, as a start toward final settlement, and despite the vice chancellor's remark that the architectural plans were the worst he had ever seen at the university, the university never agreed to the joint review;

(15)  on July 10, 1996, and in compliance with the dispute resolution procedure provided for by the contract, DalMac Construction Company gave notice to the chancellor of The Texas A&M University System that the company was appealing the vice chancellor's rejection of the claim;

(16)  on September 25, 1996, the chancellor set the dispute for arbitration in College Station, Texas, for two or three days, over DalMac Construction Company's objection that two or three days was not ample time to present all complicated engineering information necessary for an informed arbitral decision;

(17)  DalMac Construction Company and the university submitted their dispute to an arbitrator, whose March 25, 1997, decision addressed only three of the numerous issues in dispute, as the university was unwilling to arbitrate the remaining issues;

(18)  on April 14, 1997, DalMac Construction Company wrote to the university proposing a settlement, to which the chancellor responded with an offer of $19,000 on a $2.4 million claim;

(19)  on April 30, 1997, pursuant to the specified dispute resolution procedure, DalMac Construction Company appealed to the Board of Regents of The Texas A&M University System and asked for a full and fair hearing;

(20)  at the hearing before the board of regents, DalMac Construction Company was given a mere 45 minutes to discuss a claim now exceeding $3 million, and the board of regents upheld the chancellor's findings;

(21)  on July 30, 1997, the board of regents offered DalMac Construction Company $204,461, an increase over the initial $19,000 offer, due only to the university's incorrect deduction of liquidated damages;

(22)  DalMac Construction Company sought confirmation that the offer of $204,461 was the board of regents' final response;

(23)  the university has failed to pay DalMac Construction Company for construction costs and expenses incurred as a result of the university's mistakes, and the university has breached the contract it entered into with DalMac Construction Company; and

(24)  DalMac Construction Company is entitled to actual and monetary damages, including court costs and attorney's fees; now, therefore, be it

RESOLVED by the Legislature of the State of Texas, That DalMac Construction Company, Inc., is granted permission to sue the State of Texas and Texas A&M University subject to Chapter 107, Civil Practice and Remedies Code; and, be it further

RESOLVED, That the president of Texas A&M University be served process as provided by Section 107.002(a)(3), Civil Practice and Remedies Code.