88R23814 JES-F

By:  Leach H.B. No. 2265

Substitute the following for H.B. No. 2265:

By:  Metcalf C.S.H.B. No. 2265

A BILL TO BE ENTITLED

AN ACT

relating to the award of compensatory damages caused by certain delays under governmental construction contracts.

BE IT ENACTED BY THE LEGISLATURE OF THE STATE OF TEXAS:

SECTION 1.  Subchapter Z, Chapter 2252, Government Code, is amended by adding Section 2252.909 to read as follows:

Sec. 2252.909.  COMPENSATORY DAMAGES CAUSED BY GOVERNMENTAL DELAYS IN CONSTRUCTION CONTRACTS. (a) In this section:

(1)  "Compensatory damages" means the costs actually incurred by a contractor as a result of delay in the schedule that could not be reasonably mitigated by the contractor. The term does not include:

(A)  special damages;

(B)  consequential damages;

(C)  home office overhead, except overhead costs for labor as defined in the applicable construction contract;

(D)  profit or markup on indirect costs; or

(E)  the costs of performing additional work that are separately agreed to by the governmental entity and contractor in a construction contract.

(2)  "Contractor" means a person engaged in the business of developing, constructing, fabricating, repairing, altering, or remodeling improvements to real property.

(3)  "Governmental entity" means:

(A)  the state;

(B)  a municipality, county, public school district, or special-purpose district or authority;

(C)  a district, county, or justice of the peace court;

(D)  a board, commission, department, office, or other agency in the executive branch of state government, including an institution of higher education as defined by Section 61.003, Education Code;

(E)  the legislature or a legislative agency; or

(F)  the Supreme Court of Texas, the Texas Court of Criminal Appeals, a court of appeals, or the State Bar of Texas or another judicial agency having statewide jurisdiction.

(b)  A provision of a construction contract between a governmental entity and a contractor may not prohibit the award of compensatory damages to the contractor for a delay to the extent that the delay is caused solely by the governmental entity or by a party for which the governmental entity is responsible.

(c)  This section does not restrict, limit, or prohibit the inclusion of a contract provision in a construction contract prescribing requirements or conditions that must be met by a contractor to seek recovery of compensatory damages, including requirements or conditions relating to notice, justification, or a duty to mitigate or for demonstrating or proving the actual cost or schedule impact of a delay.

(d)  This section may not be waived. A purported waiver of this section in violation of this subsection is void.

(e)  This section does not apply to a construction contract for:

(1)  services related to recovery or relief from a natural disaster involving the repair or renovation of a residence; or

(2)  the construction or repair of a critical infrastructure facility, as that term is defined by Section 59.001, Business & Commerce Code, owned or operated by the governmental entity or any building, structure, improvement, appurtenance, or other facility owned by the governmental entity that is necessary to the operation of and directly related to the critical infrastructure facility.

SECTION 2.  Section 2252.909, Government Code, as added by this Act, applies only to a construction contract entered into on or after the effective date of this Act.

SECTION 3.  This Act takes effect September 1, 2023.